## Defects
Bug list
Defect ID | Module | Description | Type | Severity | Priority | Status | Created Date
DF-001 | MD-001 | The expected result 01/12/2022 is valid day, but the program show 01/12/2022 is invalid day | Coding Logic | Serious | Medium | Closed | 2022-10-24
DF-002 | MD-002 | The expected result 00/01/2022 is invalid date, but the program show 00/01/2022 is valid date | Coding Logic | Fatal | High | Closed | 2022-10-24
DF-003 | MD-003 | The expected result 32/03/2022 is invalid date, but the program show 32/03/2022 is valid date | Coding Logic | Fatal | High | Closed | 2022-10-24
DF-004 | MD-004 | The expected result 29/02/2024 is valid date, but the program show 29/02/2024 is invalid date | Coding Logic | Serious | High | Closed | 2022-10-24
DF-005 | MD-005 | The expected result 30/05/2022 is valid date, but the program show 30/05/2022 is invalid date | Coding Logic | Serious | High | Closed | 2022-10-24
DF-006 | MD-006 | The expected result 00/8/2022 is invalid date but the program show 00/8/2022 is valid date | Coding Logic | Medium | Medium | Closed | 2022-10-24
DF-007 | MD-007 | The expected result 28/2/2025 is valid date, but the program show 28/2/2025 is invalid date | Coding Logic | Medium | Medium | Closed | 2022-10-24
DF-008 | MD-008 | The expected result 30/12/2023 is valid date, but the program show 30/12/2023 is invalid date | Coding Logic | Medium | Medium | Closed | 2022-10-24
DF-009 | MD-009 | The expected result 31/8/2022 is valid date, but the program show 31/8/2023 is invalid date | Coding Logic | Medium | Medium | Closed | 2022-10-24
DF-010 | MD-010 | The expected result 30/11/2022 is valid date, but the program show 30/11/2022 is invalid date | Coding Logic | Medium | Medium | Pending | 2022-10-24
DF-011 | MD-011 | The expected result 01/01/999 is invalid date, but the program show 01/01/999 is valid date | Coding Logic | Medium | Medium | Closed | 2022-10-24
DF-012 | MD-012 | The expected result 01/01/3001 is invalid date, but the program show 01/01/3001 is valid date | Coding Logic | Medium | Medium | Closed | 2022-10-24
DF-013 | MD-013 | The expected result 02/2025 has 28 days, but the program show 02/2025 has 29 days | Coding Logic | Serious | High | Closed | 2022-10-24
DF-014 | MD-014 | The expected result 02/2024 has 29 days is true , but the program show 02/2024 has 29 days is false | Coding Logic | Medium | Medium | Closed | 2022-10-24
DF-015 | MD-015 | The expected result 9/2024 has 31 days is false , but the program show 9/2024 has 31 days is true | Coding Logic | Serious | High | Closed | 2022-10-24
DF-016 | MD-016 | The expected result 32/01/2022 is invalid date, but the program show 32/01/2022 is valid date | Coding Logic | Fatal | High | Pending | 2022-10-24
DF-017 | MD-017 | The expected result 32/12/2022 is invalid date, but the program show 32/12/2022 is valid date | Coding Logic | Fatal | High | Pending | 2022-10-24