## Defects
Bug list
Defect ID | Module | Description | Type | Severity | Priority | Status | Created Date
SDF-001 | MD-001 | The expected result is: "31/09/2022 is an invalid date" but the program show "31/09/2022 is a valid date" | Coding Logic | Serious | High | Pending | 2022-10-27
SDF-002 | MD-002 | The expected result is: "01/01/1000 is an valid date" but the program show "01/01/1000 is an invalid date" | Coding Logic | Medium | Medium | Closed | 2022-10-27
SDF-003 | MD-003 | The expected result is: "01/01/3000 is an valid date" but the program show "01/01/3000 is an invalid date" | Coding Logic | Medium | Medium | Closed | 2022-10-27
SDF-004 | MD-004 | The expected action when click Clear button is all the values in the form are cleared but it not be cleared | Coding Logic | Medium | Low | Pending | 2022-10-27
SDF-005 | MD-005 | The FPT logo in the top left corner is not display | User Interface | Cosmetic | Low | Pending | 2022-10-27
SDF-006 | MD-006 | Expected when click Close button, the program ask if "Are you sure to exit?" before close the program but it does not | Business Logic | Medium | Medium | Pending | 2022-10-27